## WBS
PROJECT WORK BREAKDOWN STRUCTURE (WBS)
Project Name: |  |  | Date:
WBS # | Task Description | Responsible | Start Date | End Date | Duration (days) | Budget | Status
1.0 | PROJECT INITIATION
1.1 | Kick-off meeting | PM |  |  | 1 |  | Not Started
1.2 | Review funding agreement | PM |  |  | 5 |  | Not Started
1.3 | Develop project charter | PM |  |  | 10 |  | Not Started
2.0 | ENVIRONMENTAL REVIEW
2.1 | Submit environmental checklist | PM |  |  | 5 |  | Not Started
2.2 | Environmental determination | Agency |  |  | 30 |  | Not Started
3.0 | DESIGN & ENGINEERING
3.1 | Procure engineering services | PM |  |  | 45 |  | Not Started
3.2 | Complete design | Engineer |  |  | 60 |  | Not Started
3.3 | Prepare bid documents | Engineer |  |  | 20 |  | Not Started
4.0 | PROCUREMENT
4.1 | Advertise bid | PM |  |  | 21 |  | Not Started
4.2 | Evaluate bids | PM |  |  | 14 |  | Not Started
4.3 | Award contract | Council |  |  | 7 |  | Not Started
5.0 | CONSTRUCTION
5.1 | Pre-construction meeting | PM |  |  | 1 |  | Not Started
5.2 | Construction activities | Contractor |  |  | 120 |  | Not Started
5.3 | Inspections | Engineer |  |  | 120 |  | Not Started
6.0 | CLOSEOUT
6.1 | Final inspection | Engineer |  |  | 5 |  | Not Started
6.2 | Submit final report | PM |  |  | 10 |  | Not Started

## Gantt Schedule
PROJECT SCHEDULE - GANTT VIEW
Project Name: |  |  | Start Date:
Task | Start | End | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12
Environmental Review
Design & Engineering
Procurement
Construction
Closeout

## Resource Allocation
RESOURCE ALLOCATION MATRIX
Resource Name | Role | Hourly Rate | Est. Hours | Est. Cost | Availability | Skills | Notes
City Administrator | Project Sponsor |  |  |  | 10% | Oversight, Approval
Public Works Director | Project Manager |  |  |  | 25% | Project Management
City Clerk | Admin Support |  |  |  | 10% | Documentation
Finance Director | Financial Oversight |  |  |  | 10% | Budget, Invoicing
Engineer (Consultant) | Technical Lead |  |  |  | Contract | Design, Inspection
Contractor | Construction |  |  |  | Contract | Construction

## Instructions
PROJECT PLANNING WORKBOOK - INSTRUCTIONS
This workbook contains four worksheets to help you plan your infrastructure project:
WBS (Work Breakdown Structure): | Lists all tasks required to complete the project
- WBS numbers help organize tasks hierarchically (1.0, 1.1, 1.2, etc.)
- Fill in responsible party, dates, budget, and status for each task
- Major phases are shaded gray
Gantt Schedule: | Visual timeline showing when tasks occur
- Shade cells to show task duration across months
- Update as project progresses
Resource Allocation: | Track people assigned to the project
- Estimate hours and costs for each resource
- Monitor availability to prevent overallocation
TIPS FOR SUCCESS:
• Update this workbook weekly
• Share with your project team and funding agency as needed
• Track actual vs. planned dates to identify delays early
• Keep a copy with your project records for closeout