## Risk Register
PROJECT RISK REGISTER
State & Federally Funded Infrastructure Projects
Project Name: | [Enter Project Name] |  |  | Grant/Award #: | [Enter Award Number] |  |  | Last Updated: | 01/07/2026
Risk ID | Date Identified | Risk Category | Risk Description | Probability (1-5) | Impact (1-5) | Risk Score | Risk Level | Response Strategy | Mitigation Actions | Risk Owner | Status | Notes
R-001 | 01/15/2026 | Compliance/Regulatory | Environmental review delays could push back construction start | 4 | 4 |  |  | Mitigate | Submit environmental docs early; maintain regular contact with reviewing agency | [Project Manager] | Open | Check status bi-weekly
R-002 | 01/15/2026 | Budget/Cost | Construction material costs may exceed estimates due to inflation | 3 | 4 |  |  | Mitigate | Include 10% contingency; get firm quotes before award | [Grant Administrator] | Open | Review monthly
R-003 | 01/15/2026 | Procurement | Competitive bidding may not yield qualified contractors in rural area | 3 | 3 |  |  | Mitigate | Expand advertising reach; consider pre-qualification | [Procurement Officer] | Open | Start procurement early
R-004 | 01/15/2026 | Schedule | Davis-Bacon compliance documentation delays contractor payments | 2 | 3 |  |  | Avoid | Provide contractor training on certified payroll requirements | [Project Manager] | Open | Include in pre-construction meeting
R-005 | 01/15/2026 | External | Key staff turnover during project execution | 2 | 4 |  |  | Transfer | Cross-train staff; document all procedures | [City Manager] | Monitoring | Update succession plan
R-006
R-007
R-008
R-009
R-010
R-011
R-012
R-013
R-014
R-015
R-016
R-017
R-018
R-019
R-020
R-021
R-022
R-023
R-024
R-025

## Risk Matrix
PROBABILITY / IMPACT MATRIX
Use this matrix to determine Risk Score: Probability x Impact
IMPACT
PROBABILITY |  | 1 | 2 | 3 | 4 | 5
| 5 | 5 | 10 | 15 | 20 | 25
| 4 | 4 | 8 | 12 | 16 | 20
| 3 | 3 | 6 | 9 | 12 | 15
| 2 | 2 | 4 | 6 | 8 | 10
| 1 | 1 | 2 | 3 | 4 | 5
RISK LEVEL LEGEND
Critical (16-25)
High (9-15)
Medium (4-8)
Low (1-3)
PROBABILITY SCALE
| 5 - Almost Certain | >90% chance of occurring
| 4 - Likely | 60-90% chance of occurring
| 3 - Possible | 30-60% chance of occurring
| 2 - Unlikely | 10-30% chance of occurring
| 1 - Rare | <10% chance of occurring
IMPACT SCALE
| 5 - Severe | Project failure; grant funds returned; >25% budget overrun
| 4 - Major | Significant delays (>3 months); 15-25% budget overrun; major scope reduction
| 3 - Moderate | Moderate delays (1-3 months); 5-15% budget overrun; some scope reduction
| 2 - Minor | Minor delays (<1 month); <5% budget overrun; minimal impact
| 1 - Insignificant | No meaningful impact on project objectives

## Risk Categories
COMMON RISK CATEGORIES FOR INFRASTRUCTURE PROJECTS
Category | Description | Examples
Schedule | Risks that could delay project completion | Weather delays, permit delays, contractor availability, material delivery delays
Budget/Cost | Risks that could increase project costs | Material price increases, change orders, unexpected site conditions, inflation
Scope | Risks to project scope or deliverables | Scope creep, unclear requirements, stakeholder changes, design errors
Compliance/Regulatory | Risks related to federal/state requirements | Environmental review delays, Davis-Bacon violations, BABA non-compliance, audit findings
Procurement | Risks in the bidding and contracting process | No qualified bidders, bid protests, contractor default, subcontractor issues
Technical | Risks related to technical aspects of the project | Design defects, equipment failures, technology changes, construction quality
Environmental | Environmental and site-related risks | Contamination discovery, endangered species, wetland issues, archaeological finds
Stakeholder | Risks from project stakeholders | Community opposition, political changes, partner disagreements, utility conflicts
Resource | Risks related to project resources and staff | Staff turnover, skill gaps, competing priorities, contractor capacity
External | External factors outside project control | Economic downturn, natural disasters, supply chain disruptions, regulatory changes
FEDERAL COMPLIANCE REMINDER
For federally funded projects, pay special attention to compliance risks. Common issues that result in grant funds being returned include: starting work before environmental clearance, skipping competitive procurement, not documenting Davis-Bacon compliance, and making unauthorized scope changes.
GRANT OPPORTUNITIES FOR CAPACITY BUILDING
USDA Rural Community Development Initiative (RCDI) | $50,000-$500,000 for capacity building
USDA Rural Business Development Grants | Up to $500,000 for rural business/community projects
EDA Public Works & Economic Adjustment Assistance | Planning and technical assistance grants
EDA Disaster Supplemental - Readiness Path | Capacity building for disaster recovery
Business Oregon Technical Assistance | State resources for Oregon communities